## Cost
Task Id | Task Name | Distribution | Minimum | Most Likely | Maximum
0 | Monitor, Control & Manage Project | Normal | 34340.625 | 38156.25 | 47695.3125
1 | Start | No Distribution |  | 0
2 | Kickoff Project/Develop Project Plan | No Distribution |  | 10500
3 | Gather Requirements | Pert | 4050 | 4500 | 5625
4 | Design Prototype | Triangular | 20250 | 22500 | 28125
5 | Get Customer Sign-off 1 | No Distribution |  | 750
6 | Build Prototype: Trial 1 | Pert | 30250 | 32500 | 38125
7 | Test Prototype: Trial 1 | Pert | 8100 | 9000 | 11250
8 | Revise/Test Prototype: Trial 2 | Pert | 13050 | 14500 | 18125
9 | Finalize Design | Pert | 8100 | 9000 | 11250
10 | Get Customer Sign-off 2 | No Distribution |  | 750
11 | Prepare Application | Pert | 5400 | 6000 | 7500
12 | Submit Application | No Distribution |  | 1500
13 | Receive Approval | No Distribution |  | 0
14 | Select Suppliers | Pert | 3375 | 3750 | 4687.5
15 | Negotiate/Sign Agreements | Pert | 4050 | 4500 | 5625
16 | Procure Equipment/Materials | Triangular | 23850 | 26500 | 33125
17 | Get Executive Sign-off 3 | No Distribution |  | 1125
18 | Ramp-up for Production | Pert | 27000 | 30000 | 37500
19 | Perform Production Testing | Pert | 8100 | 9000 | 11250
20 | Launch | No Distribution |  | 3000
21 | Finish | No Distribution |  | 0
22 | Resubmit Application | No Distribution |  | 0
Note: Please do not forget to provide the input data on the spreadsheet on the next tab.

## Risk Register
Cost Impact, $
Risk Id | Risk Name | Threat or Opportunity | Risk Id Mutually Exclusive to | Risk Frequency Distribution | p/lambda | Cost Impact Distribution | Cost Minimum | Cost Most Likely | Cost Maximum | Cost Task Id Impacted | Cost Operator
1 | Application is rejected. | Threat | 4 | Bernoulli | 0.3 | No Impact |  |  |  | 22 | Add
2 | Trial 1 of prototype testing is a total failure. | Threat | 5 | Bernoulli | 0.3 | Pert | 12150 | 13500 | 16875 | 8 | Add
3 | Supply chain disruptions are caused by a hurricane(s). | Threat |  | Poisson | 0.25 | Pert | 2025 | 2250 | 2812.5 | 16 | Maximum
4 | Application is approved quickly. | Opportunity | 1 | Bernoulli | 0.2 | No Impact |  |  |  | 13 | Substract
5 | Trial 1 of prototype testing is a total success. | Opportunity | 2 | Bernoulli | 0.1 | No Distribution |  | 0 |  | 8 | Minimum

## parameters
Cost Parameters
Allowed Distribution for Cost Modeling
Distribution Name | Minimum | Most Likely | Maximum | Documentation
No Distribution | Locked |  | Locked
Normal |  | Locked
Pert
Triangular
Uniform |  | Locked
Risk Parameters
Allowed Distribution for Risk Frequency Modeling
Distribution Name | p/lambda | Documentation
Bernoulli
Poisson
Allowed Distribution for Risk Impact Modeling
Distribution Name | Minimum | Most Likely | Maximum | Documentation
No Distribution | Locked |  | Locked
No Impact | Locked | Locked | Locked
Normal |  | Locked
Pert
Triangular
Uniform |  | Locked
Allowed Operator for Schedule / Cost Impact
Allowed Operator
Add
Maximum
Minimum
Substract