## Schedule
Task Id | Task Name | Distribution | Minimum | Most Likely | Maximum | Predecessor
0 | Monitor, Control & Manage Project | Project Duration |  | 255
1 | Start | No Distribution |  | 0
2 | Kickoff Project/Develop Project Plan | No Distribution |  | 5 |  | 1
3 | Gather Requirements | Pert | 13.5 | 15 | 18.75 | 2
4 | Design Prototype | Triangular | 22.5 | 25 | 31.25 | 3
5 | Get Customer Sign-off 1 | No Distribution |  | 5 |  | 4
6 | Build Prototype: Trial 1 | Pert | 22.5 | 25 | 31.25 | 5
7 | Test Prototype: Trial 1 | Pert | 9 | 10 | 12.5 | 6
8 | Revise/Test Prototype: Trial 2 | Pert | 13.5 | 15 | 18.75 | 7
9 | Finalize Design | Pert | 9 | 10 | 12.5 | 8
10 | Get Customer Sign-off 2 | No Distribution |  | 5 |  | 9
11 | Prepare Application | Pert | 18 | 20 | 25 | 5
12 | Submit Application | No Distribution |  | 5 |  | 10 11
13 | Receive Approval | Triangular | 54 | 60 | 75 | 12 22
14 | Select Suppliers | Pert | 45 | 50 | 62.5 | 5
15 | Negotiate/Sign Agreements | Pert | 27 | 30 | 37.5 | 14
16 | Procure Equipment/Materials | Triangular | 36 | 40 | 50 | 15
17 | Get Executive Sign-off 3 | No Distribution |  | 5 |  | 13 16
18 | Ramp-up for Production | Pert | 45 | 50 | 62.5 | 17
19 | Perform Production Testing | Pert | 13.5 | 15 | 18.75 | 18
20 | Launch | No Distribution |  | 5 |  | 19
21 | Finish | No Distribution |  | 0 |  | 20
22 | Resubmit Application | No Distribution |  | 0 |  | 12
Note: Please do not forget to provide the input data on the spreadsheet on the next tab.

## Cost
|  |  | Labor Cost ( = Task Duration * Daily Cost) |  |  |  | Fixed Cost
Task Id | Project/Phases/Tasks | Most Likely Task Duration, days | No. of Resources Assigned | Effort, hr/d/person | Salary, $/h/person | Daily Cost, $/d | Distribution | Minimum | Most Likely | Maximum | Total Task Cost | % of Project Cost
Project Zulu
1 | Start | 0 |  |  |  | 0 |  |  |  |  | 0 | 0%
Project Management
0 | Monitor, Control & Manage Project | 255 | 1 | 1.5 | 75 | 112.5 |  |  |  |  | 28687.5 | 12.53%
2 | Kickoff Project/Develop Project Plan | 5 | 7 | 4 | 75 | 2100 |  |  |  |  | 10500 | 4.586%
Initial Design
3 | Gather Requirements | 15 | 1 | 4 | 75 | 300 |  |  |  |  | 4500 | 1.965%
4 | Design Prototype | 25 | 2 | 6 | 75 | 900 |  |  |  |  | 22500 | 9.827%
5 | Get Customer Sign-off 1 | 5 | 2 | 1 | 75 | 150 |  |  |  |  | 750 | 0.3276%
Prototyping
6 | Build Prototype: Trial 1 | 25 | 2 | 6 | 75 | 900 | Pert | 9000 | 10000 | 12500 | 32500 | 14.19%
7 | Test Prototype: Trial 1 | 10 | 2 | 6 | 75 | 900 |  |  |  |  | 9000 | 3.931%
8 | Revise/Test Prototype: Trial 2 | 15 | 2 | 6 | 75 | 900 | No Distribution |  | 1000 |  | 14500 | 6.333%
Final Design
9 | Finalize Design | 10 | 2 | 6 | 75 | 900 |  |  |  |  | 9000 | 3.931%
10 | Get Customer Sign-off 2 | 5 | 2 | 1 | 75 | 150 |  |  |  |  | 750 | 0.3276%
Regulatory Assistance
11 | Prepare Application | 20 | 1 | 4 | 75 | 300 |  |  |  |  | 6000 | 2.62%
12 | Submit Application | 5 | 1 | 4 | 75 | 300 |  |  |  |  | 1500 | 0.6551%
13 | Receive Approval | 60 |  |  | 75 | 0 |  |  |  |  | 0 | 0%
Procurement
14 | Select Suppliers | 50 | 1 | 1 | 75 | 75 |  |  |  |  | 3750 | 1.638%
15 | Negotiate/Sign Agreements | 30 | 2 | 1 | 75 | 150 |  |  |  |  | 4500 | 1.965%
16 | Procure Equipment/Materials | 40 | 1 | 0.5 | 75 | 37.5 | No Distribution |  | 25000 |  | 26500 | 11.57%
Launch
17 | Get Executive Sign-off 3 | 5 | 3 | 1 | 75 | 225 |  |  |  |  | 1125 | 0.4913%
18 | Ramp-up for Production | 50 | 2 | 4 | 75 | 600 |  |  |  |  | 30000 | 13.1%
19 | Perform Production Testing | 15 | 2 | 4 | 75 | 600 |  |  |  |  | 9000 | 3.931%
20 | Launch | 5 | 2 | 4 | 75 | 600 |  |  |  |  | 3000 | 1.31%
21 | Finish | 0 |  |  |  | 0 |  |  |  |  | 0 | 0%
22 | Resubmit Application | 0 |  |  |  | 0 |  |  |  |  | 0 | 0%
[7 empty] | Sum Cost of All Tasks: |  |  |  | 218062.5 | 95.24%
[7 empty] | PM cost as Percentage of Sum Cost of All Tasks: |  |  |  | 5%
[7 empty] | Total Project Cost: |  |  |  | 228965.625 | 100%
| Note: | Hawkeye Code will only read column A(Task Id), G(Daily Cost), H-K(Fixed Cost), and PM percentage cost cell(L35 in Example Problem Excel)
other columns for display purpose only.
Note: Please do not forget to provide the input data on the spreadsheet on the next tab.

## Risk Register
[6 empty] | Schedule Impact, days | [5 empty] | Cost Impact, $
Risk Id | Risk Name | Threat or Opportunity | Risk Id Mutually Exclusive to | Risk Frequency Distribution | p/lambda | Schedule Impact Distribution | Schedule Minimum | Schedule Most Likely | Schedule Maximum | Schedule Task Id Impacted | Schedule Operator | Cost Impact Distribution | Cost Minimum | Cost Most Likely | Cost Maximum | Cost Task Id Impacted | Cost Operator
1 | Application is rejected. | Threat | 4 | Bernoulli | 0.3 | Pert | 13.5 | 15 | 18.75 | 22 | Add | No Impact
2 | Trial 1 of prototype testing is a total failure. | Threat | 5 | Bernoulli | 0.3 | Pert | 13.5 | 15 | 18.75 | 8 | Add | No Distribution |  | 1000 |  | 8 | Add
3 | Supply chain disruptions are caused by a hurricane(s). | Threat |  | Poisson | 0.25 | Pert | 54 | 60 | 75 | 16 | Maximum | Pert | 4500 | 5000 | 6250 | 16 | Add
4 | Application is approved quickly. | Opportunity | 1 | Bernoulli | 0.2 | Pert | 18 | 20 | 25 | 13 | Substract | No Impact
5 | Trial 1 of prototype testing is a total success. | Opportunity | 2 | Bernoulli | 0.1 | No Distribution |  | 0 |  | 8 | Minimum | No Distribution |  | 1000 |  | 8 | Substract

## parameters
Schedule Parameters
Allowed Distribution for Schedule Duration Modeling
Distribution Name | Minimum | Most Likely | Maximum | Documentation
No Distribution | Locked |  | Locked
Normal |  | Locked
Pert
Project Duration | Locked |  | Locked
Triangular
Uniform |  | Locked
Cost Parameters
Allowed Distribution for Cost Modeling
Distribution Name | Minimum | Most Likely | Maximum | Documentation
No Distribution | Locked |  | Locked
Normal |  | Locked
Pert
Triangular
Uniform |  | Locked
Risk Parameters
Allowed Distribution for Risk Frequency Modeling
Distribution Name | p/lambda | Documentation
Bernoulli
Poisson
Allowed Distribution for Risk Impact Modeling
Distribution Name | Minimum | Most Likely | Maximum | Documentation
No Distribution | Locked |  | Locked
No Impact | Locked | Locked | Locked
Normal |  | Locked
Pert
Triangular
Uniform |  | Locked
Allowed Operator for Schedule / Cost Impact
Schedule |  | Cost
Add |  | Add
Maximum |  | Substract
Minimum
Substract