## Cost
Task Id | Task Name | Distribution | Minimum | Most Likely | Maximum
0 | Monitor, Control & Manage Project | No Distribution |  | 38156.25
1 | Start | No Distribution |  | 0
2 | Kickoff Project/Develop Project Plan | No Distribution |  | 10500
3 | Gather Requirements | No Distribution |  | 4500
4 | Design Prototype | No Distribution |  | 22500
5 | Get Customer Sign-off 1 | No Distribution |  | 750
6 | Build Prototype: Trial 1 | No Distribution |  | 32500
7 | Test Prototype: Trial 1 | No Distribution |  | 9000
8 | Revise/Test Prototype: Trial 2 | No Distribution |  | 14500
9 | Finalize Design | No Distribution |  | 9000
10 | Get Customer Sign-off 2 | No Distribution |  | 750
11 | Prepare Application | No Distribution |  | 6000
12 | Submit Application | No Distribution |  | 1500
13 | Receive Approval | No Distribution |  | 0
14 | Select Suppliers | No Distribution |  | 3750
15 | Negotiate/Sign Agreements | No Distribution |  | 4500
16 | Procure Equipment/Materials | No Distribution |  | 26500
17 | Get Executive Sign-off 3 | No Distribution |  | 1125
18 | Ramp-up for Production | No Distribution |  | 30000
19 | Perform Production Testing | No Distribution |  | 9000
20 | Launch | No Distribution |  | 3000
21 | Finish | No Distribution |  | 0
22 | Resubmit Application | No Distribution |  | 0

## parameters
Cost Parameters
Allowed Distribution for Cost Modeling
Distribution Name | Minimum | Most Likely | Maximum | Documentation
No Distribution | Locked |  | Locked
Normal |  | Locked
Pert
Project Duration | Locked |  | Locked
Triangular
Uniform |  | Locked
Risk Parameters
Allowed Distribution for Risk Frequency Modeling
Distribution Name | p/lambda | Documentation
Bernoulli
Poisson
Allowed Distribution for Risk Impact Modeling
Distribution Name | Minimum | Most Likely | Maximum | Documentation
No Distribution | Locked |  | Locked
No Impact | Locked | Locked | Locked
Normal |  | Locked
Pert
Triangular
Uniform |  | Locked
Allowed Operator for Schedule / Cost Impact
Allowed Operator
Add
Maximum
Minimum
Substract