## Schedule
Task Id | Task Name | Distribution | Minimum | Most Likely | Maximum | Predecessor
0 | Monitor, Control & Manage Project | No Distribution |  | 255
1 | Start | No Distribution |  | 0
2 | Kickoff Project/Develop Project Plan | No Distribution |  | 5 |  | 1
3 | Gather Requirements | No Distribution |  | 15 |  | 2
4 | Design Prototype | No Distribution |  | 25 |  | 3
5 | Get Customer Sign-off 1 | No Distribution |  | 5 |  | 4
6 | Build Prototype: Trial 1 | No Distribution |  | 25 |  | 5
7 | Test Prototype: Trial 1 | No Distribution |  | 10 |  | 6
8 | Revise/Test Prototype: Trial 2 | No Distribution |  | 15 |  | 7
9 | Finalize Design | No Distribution |  | 10 |  | 8
10 | Get Customer Sign-off 2 | No Distribution |  | 5 |  | 9
11 | Prepare Application | No Distribution |  | 20 |  | 5
12 | Submit Application | No Distribution |  | 5 |  | 10 11
13 | Receive Approval | No Distribution |  | 60 |  | 12 22
14 | Select Suppliers | No Distribution |  | 50 |  | 5
15 | Negotiate/Sign Agreements | No Distribution |  | 30 |  | 14
16 | Procure Equipment/Materials | No Distribution |  | 40 |  | 15
17 | Get Executive Sign-off 3 | No Distribution |  | 5 |  | 13 16
18 | Ramp-up for Production | No Distribution |  | 50 |  | 17
19 | Perform Production Testing | No Distribution |  | 15 |  | 18
20 | Launch | No Distribution |  | 5 |  | 19
21 | Finish | No Distribution |  | 0 |  | 20
22 | Resubmit Application | No Distribution |  | 0 |  | 12

## parameters
Schedule Parameters
Allowed Distribution for Schedule Duration Modeling
Distribution Name | Minimum | Most Likely | Maximum | Documentation
No Distribution | Locked |  | Locked
Normal |  | Locked
Pert
Project Duration | Locked |  | Locked
Triangular
Uniform |  | Locked
Risk Parameters
Allowed Distribution for Risk Frequency Modeling
Distribution Name | p/lambda | Documentation
Bernoulli
Poisson
Allowed Distribution for Risk Impact Modeling
Distribution Name | Minimum | Most Likely | Maximum | Documentation
No Distribution | Locked |  | Locked
No Impact | Locked | Locked | Locked
Normal |  | Locked
Pert
Triangular
Uniform |  | Locked
Allowed Operator for Schedule / Cost Impact
Schedule |  | Cost
Add |  | Add
Maximum |  | Substract
Minimum
Substract